## Sheet1
|  | Members | Đặng Minh Thuận
Ngô Tường Vinh
Phan Lê Trọng Nghĩa
|  | Class | SE1401
|  | Subject | PRJ311 - Java Desktop Applications
|  | Project | Build a Java application to manage the goods receipt and goods delivery of a storage of a grocery's store
TASK ROLE
SN | Task |  |  | PIC | Status | Percent of completion
1 | Select topic for assignment |  |  | All members | Finished | 100%
2 | Dividing tasks |  |  | Nghĩa | Finished | 100%
3 | Make project's introduction (document) |  |  | Vinh | Finished | 70%
4 | Make project's description and plan (document) |  |  | Nghĩa | Finished | 70%
5 | Make project's requirement specification (document) |  |  | Thuận | Finished | 70%
6 | Describe and draw flow charts for each algorithm (document) |  |  | Nghĩa + Thuận | Not finished | 50%
7 | Draw use-case diagram (document) |  |  | Nghĩa + Thuận | Finished | 70%
8 | Make unit testing check list (document) |  |  | Thuận | Finished | 80%
9 | Checking document format and content |  |  | Nghĩa | Not finished | 50%
10 | Login function for user (admin / staffs) (code) |  |  | Vinh | Finished | 70%
11 | Modify products function for admin (code) |  |  | Nghĩa | Finished | 70%
12 | Modify suppliers function for admin (code) |  |  | Vinh | Finished | 70%
13 | Manage employee information for admin and export into Excel (code) |  |  | Nghĩa + Thuận | Not finished | N/A
14 | Manage goods receipt for staff (code) |  |  | Thuận | Finished | 70%
15 | Manage goods delivery for staff (code) |  |  | Thuận | Finished | 70%
16 | Check the existence of all products in the storage (code) |  |  | Thuận | Finished | 70%
17 | Export the table of all existence products in the storage into Excel (code) |  |  | Nghĩa + Thuận | Finished | 80%
18 | Calculate the amount of salary paid for staffs in a day (code) |  |  | Vinh | Not finished | N/A
19 | Design the GUI of the application logically and be easy to use (code) |  |  | Nghĩa | Not finished | 40%